## Table 2
UX/UI Research & Concept | Estimation title UX/UI Research, Concept, User Experience, User Interface Design, Copywriting, Project Management 2022-01-08 | Backend Development | Project Management | TOTAL
|  |  |  | Desktop | Mobile | Desktop | Tablet | Mobile
MAN HOURS |  | 121 |  | 221 | 4 | 194 | 2 | 14 | 28 | 51.2 | 51.42 | 635.2
CONCEPT PHASE | [11 empty] | 72
WORKSHOPS (+ PREPARATION) |  | 24 | [8 empty] | 0 | 24
Workshop 1 - process mapping |  | 12
Workshop 2 - design meeting (architecture) - assumptions |  | 12
ARCHITECTURE |  | 48 | [8 empty] | 0 | 48
User flow |  | 24
Lo-fi mockups |  | 24
Web PLATFORM | [11 empty] | 286.79
LANDING PAGE |  | 4 |  | 8 | 2 | 8 | 2 | 4 | 8 | 3.6 | 3.56 | 43.16
PLATFORM ENTRY |  | 2 |  | 6 | 2 | 6 |  | 2 | 2 | 2 | 2 | 24
Registration processes Login processes
SYSTEM MAIL |  | 2 |  | 3 |  | 2 |  |  | 2 | 0.9 | 0.79 | 10.69
DASHBOARD |  | 4 |  | 16 |  | 16 |  |  | 1 | 3.7 | 3.67 | 44.37
Global view Local view
SALES PROCESS |  | 4 |  | 26 |  | 24 |  |  | 1 | 5.5 | 5.65 | 66.15
Upsell
INVOICES |  | 2 |  | 12 |  | 8 |  |  | 1 | 2.3 | 2.33 | 27.63
REPORTS |  | 2 |  | 12 |  | 8 |  |  | 1 | 2.3 | 2.33 | 27.63
Filters
DISCOUNTS |  | 2 |  | 6 |  | 4 |  |  | 1 | 1.3 | 1.23 | 15.53
SETTINGS |  | 2 |  | 12 |  | 8 |  |  | 1 | 2.3 | 2.33 | 27.63
Admin Platform | [11 empty] | 298.79
PLATFORM ENTRY |  | 1 |  | 6 |  | 6 |  |  | 1 | 1.4 | 1.44 | 16.84
DASHBOARD |  | 4 |  | 16 |  | 16 |  |  | 2 | 3.8 | 3.78 | 45.58
INVOICES |  | 2 |  | 8 |  | 8 |  |  | 1 | 1.9 | 1.89 | 22.79
REPORTS |  | 2 |  | 8 |  | 8 |  |  | 1 | 1.9 | 1.89 | 22.79
Filters
PARTNER MANAGEMENT |  | 4 |  | 24 |  | 16 |  |  | 1 | 4.5 | 4.55 | 54.05
Adding / Editing Limits
PRODUCTS MANAGEMENT |  | 4 |  | 26 |  | 16 |  |  | 1 | 4.7 | 4.77 | 56.47
Also for each partner
PAYMENT METHODS MANAGEMENT |  | 3 |  | 12 |  | 8 |  |  | 1 | 2.4 | 2.34 | 28.74
COMMISIONS |  | 3 |  | 12 |  | 8 |  |  | 1 | 2.4 | 2.34 | 28.74
SETTINGS |  | 2 |  | 8 |  | 8 |  |  | 1 | 1.9 | 1.89 | 22.79
ADDITIONAL WORK | [11 empty] | 50.82
STYLE GUIDE | [5 empty] | 16 |  | 8 |  | 2.4 | 2.64 | 29.04
For Developers
PREPARATION OF PRODUCTION FILES | [5 empty] | 12 |  | 6 |  | 1.8 | 1.98 | 21.78
SOFTWARE TESTING |  | 5 |  | 5 |  | 5 |  | 5 | 5 | 5 | 5 | 5